## HLDD
High Level Design Document (HLDD)
Project Information
Project Title | Coding for Good
Project Purpose | Create a web-based course that when completed will allow Brownie and Junior Girl Scouts to earn the 3 Coding for Good badges.
Project Target Launch Date | 2026-08-01
Roles & Responsibilities
Project Owner | Jennifer Swanson
Project Stakeholder(s) | Jennifer Swanson
Subject Matter Experts | Jennifer Swanson, Girl Scout Volunteer Toolkit (VTK), Brownie and Junior Coding for Good Booklets
Instructional Designer | Jennifer Swanson
Developers | Jennifer Swanson
Trainers | N/A
Other Reviews | N/A
Audience, Goals, & Objectives
Target Audience | Brownies (7-8 year olds) and Juniors (9-10 year olds)
Project Goal | After completing this program, Brownie and Junior-level girl scouts will know how people create code that tells computers what to do.
50% of the girls who complete the course will want to learn more about coding.
Learning Objectives | After completing this training, learners will be able to…
| 1 | Create algorithms for a computer that follows a sequence
| 2 | Use loops to improve your algorithm
| 3 | Use events to make things happen
| 4 | Keep your code interesting with conditionals
| 5 | Learn about women in computer science
| 6 | Create you own set of commands that use events
| 7 | Create your own set of commands that use conditionals
| 8 | Discover how game design can be used "for good"
| 9 | Explorer tools used to develop digital games
| 10 | Plan a maze game
| 11 | Build, test, and improve your maze game using iteration
| 12 | Share your game with others
| 13 | Discover how apps can be used "for good"
| 14 | Decompose the needs of your app user
| 15 | Design your app screens
| 16 | Create algorithms for your app that include events
| 17 | Include conditionals in your app design
| 18 | Share and improve your app with user feedback
Project Deliverables
Deliverable 1 | Storyline 360 Line Course
Deliverable 2 | PB&J Video
Deliverable 3
Project Milestones
4/10 - 4/30 | Initial analysis and training design
5/1 - 5/15 | Development
N/A | LMS configuration and testing
N/A | Train the trainer
N/A | Delivery and evaluation of pilot training
8/1 - 9/1 | Training delivery to all target learners
9/2 - 9/10 | Evaluation and project retrospective
Implementation & Measurement
Implementation Plan | Once the training has been built, it will be shared with a group of 5 girls to take the training and earn their badges. Once they complete the training we will receive feedback from them and make changes to the program as needed.
A training link will be provided to each girl that they can use to access the training from their own home computer. They will have 4 weeks to complete the training.
Evaluation Plan | Completion of the self-paced learning.
Girls Evaluation feedback on how they liked the training, was it fun, was it easy, did the understand the concepts?
Are the girls interested in learning more about coding and continue pursuing more coding knowledge.
In-Scope (Deliverables) | Teaching basic coding concepts and logic
Teaching Pseudo-Code
Showing girls examples of real code
Out-of-Scope (Exclusions) | Teach girls a coding language
Having the girls create real code in a coding language
Constraints (Limits) | Time for development
Don't own a copy of Storyline, so when I get to that step, I will have to be fast with the development or risk not finishing the project
Won't have access to Storyline to make adjustments to content based on feedback.
Risks (Uncertainties) | This is a side project and so it is in danger of not being worked on in favor of other projects.
Risk not being able to finish development if it takes longer than the amount of time I have access to Storyline.
Risk trying to add too much information and being too technical for young girls to understand the concepts.

## Project Timeline
Project Timeline
| Date Assigned | Date Due | Date Completed | Assigned To | Status | Description
| 2026-04-14 | 2026-04-17 | 2026-04-14 | Jennifer Swanson | Complete | Create HLDD Template
| 2026-04-14 | 2026-04-17 | 2026-04-14 | Jennifer Swanson | Complete | Create HLDD
| 2026-04-14 | 2026-04-17 |  | Jennifer Swanson | In Progress | Create Storyline Girl Scout Section of Portfolio Site
| 2026-04-14 | 2026-04-17 |  | Jennifer Swanson | In Progress | Gather information to create Rough Draft
| 2026-04-14 | 2026-04-17 |  | Jennifer Swanson | In Progress | Create Storyboard
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Update Portfolio 2
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Design Project Layout Template
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Create all Graphics for Project
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Develop all Videos for the Project
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Update Portfolio 3
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Develop all downloadable documents for the Project
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Download Storyline and see how long can access
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Develop course in Storyline 360
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Test course
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Publish course
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Update Portfolio 4
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Review course and implement feedback
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Have girl scouts take course and gather feedback
| 2026-04-14 |  |  | Jennifer Swanson | Not Started | Update Profolio with final content

## Update Log
Update Log
Date | User | Description
2026-04-14 | Jennifer Swanson | Created HLDD

## Not for Use - Don't Delete
Not Started
In Progress
Complete
Descoped